## Overview
Credit Foundation Model - 60 Day Roadmap
Objective | Build a credit-data-specific foundation model based on NVIDIA transaction-foundation-model blueprint
Compute Window | 60 days
Available Hardware | 8x NVIDIA H100, 640GB VRAM total
Primary Success Metric | Measurable lift from self-supervised credit embeddings vs raw-feature baselines
Recommended Main Model | Credit-TFM-M, 100M-250M parameters, 4k-8k context
Primary Downstream Tasks | Default / delinquency, prepayment, cure, segmentation, anomaly detection
Definition of Done | Tokenizer, trained checkpoint, embedding pipeline, downstream benchmark, leakage audit, model/data cards
Phase | Days | Focus | Primary Deliverables | Exit Criteria | Owner | Status | Notes
0 | 1-2 | Setup and decision log | Repo fork, experiment tracking, data dictionary, model card template | Environment reproducible and objective confirmed |  | Not Started
1 | 3-8 | Credit event schema | Canonical event schema, leakage inventory, temporal split design | Approved observation-time field list and train/val/test split |  | Not Started
2 | 9-14 | Baselines | XGBoost/LightGBM/logistic baselines, metrics table, DQ report | Strong baseline and trustworthy labels |  | Not Started
3 | 15-22 | Credit tokenizer v1 | Tokenizer config, vocabulary, token reports, train/val/test corpora | 95-99% sequences fit chosen context or windowing policy defined |  | Not Started
4 | 23-34 | Pretraining scale-up | 30M, 100M-250M checkpoints, loss curves, GPU utilization report | Stable training and validation loss; candidate checkpoint selected |  | Not Started
5 | 35-43 | Embedding extraction and downstream eval | Embedding parquet, downstream benchmarks, comparison dashboard | Embeddings show lift or clear failure diagnosis |  | Not Started
6 | 44-50 | Tokenizer v2 and ablations | Ablation table, selected tokenizer, leakage audit | Final tokenizer/model candidate selected |  | Not Started
7 | 51-56 | Prototype productization | Batch embedding pipeline, scoring pipeline, demo portfolio report | Repeatable commands for train/infer/score |  | Not Started
8 | 57-60 | Final validation and handoff | Technical report, model card, data card, demo, v2 roadmap | Handoff package complete |  | Not Started

## Roadmap
Phase | Start Day | End Day | Workstream | Task | Deliverable | Dependency | Owner | Status | Priority | Evidence / Link | Notes
0 | 1 | 2 | Project Mgmt | Fork blueprint repo and create internal project repo | credit-foundation-model repo |  |  | Not Started | High
0 | 1 | 2 | Infrastructure | Provision H100 environment and validate 8-GPU torchrun | GPU smoke-test log |  |  | Not Started | High
0 | 1 | 2 | MLOps | Set up experiment tracking and checkpoint storage | Tracking dashboard / artifact paths |  |  | Not Started | High
0 | 1 | 2 | Governance | Create model card, data card, and decision-log templates | Templates in reports/ |  |  | Not Started | Medium
1 | 3 | 4 | Data Engineering | Inventory credit datasets and fields | Data inventory and field ownership map | Repo setup |  | Not Started | High
1 | 3 | 6 | Data Engineering | Define canonical entity hierarchy: borrower, loan, observation | Credit entity schema | Data inventory |  | Not Started | High
1 | 4 | 8 | Risk / Data | Define event taxonomy: observation, payment, delinquency, default, cure, prepayment, restructuring | credit_event_schema.md | Entity schema |  | Not Started | High
1 | 5 | 8 | Risk / Data | Build observation-time leakage inventory | Leakage audit v0 | Field inventory |  | Not Started | High
1 | 6 | 8 | Data Science | Design temporal train / validation / test split | Split design document | Entity schema |  | Not Started | High
2 | 9 | 11 | Data Science | Build raw-feature baseline dataset by observation date | Baseline modeling table | Split design |  | Not Started | High
2 | 10 | 13 | Data Science | Train logistic regression, XGBoost / LightGBM baselines | Baseline metrics table | Baseline dataset |  | Not Started | High
2 | 12 | 14 | Validation | Evaluate ROC-AUC, PR-AUC, KS, Gini, calibration, lift@K | Baseline evaluation report | Baseline models |  | Not Started | High
2 | 13 | 14 | Governance | Review labels, leakage, and baseline quality | Go / no-go decision | Evaluation report |  | Not Started | High
3 | 15 | 17 | Tokenizer | Implement categorical, numeric bucket, temporal, and event token classes | credit_tokenizer.py | Event schema |  | Not Started | High
3 | 16 | 19 | Tokenizer | Create credit tokenizer configuration and bucket definitions | credit_tokenizer.yaml | Leakage audit |  | Not Started | High
3 | 18 | 21 | Data Engineering | Generate train / validation / test decoder corpus files | Corpus text files | Tokenizer v1 |  | Not Started | High
3 | 20 | 22 | Validation | Produce token frequency, rare-token, OOV, and sequence length reports | Tokenizer QA report | Corpus files |  | Not Started | High
4 | 23 | 24 | Training | Run 1-GPU smoke test for 1k-5k steps | Smoke-test checkpoint and logs | Corpus files |  | Not Started | High
4 | 25 | 27 | Training | Train Credit-TFM-S around 30M parameters on 8 GPUs | Small checkpoint | Smoke test |  | Not Started | High
4 | 28 | 31 | Training | Train Credit-TFM-M around 100M-250M parameters | Medium checkpoint | Small checkpoint |  | Not Started | High
4 | 30 | 34 | Training | Run context length comparison: 2k, 4k, 8k | Context ablation results | Medium config |  | Not Started | Medium
4 | 32 | 34 | MLOps | Summarize loss, perplexity, throughput, utilization | Training report | Training runs |  | Not Started | Medium
5 | 35 | 37 | Inference | Extract embeddings using last-token, mean, event-anchor, and window pooling | Embedding parquet files | Candidate checkpoints |  | Not Started | High
5 | 37 | 41 | Data Science | Train downstream models using embeddings only and raw+embeddings | Downstream model artifacts | Embedding files |  | Not Started | High
5 | 40 | 43 | Validation | Compare lift, calibration, stability by vintage and segment | Embedding lift report | Downstream models |  | Not Started | High
6 | 44 | 46 | Tokenizer | Run tokenizer ablations: quantile vs domain buckets, macro/no macro, collateral/no collateral | Tokenizer ablation table | Evaluation report |  | Not Started | Medium
6 | 46 | 48 | Training | Run model ablations: 30M vs 100M vs 250M, 4k vs 8k context | Model ablation table | Tokenizer variants |  | Not Started | Medium
6 | 48 | 50 | Governance | Complete leakage audit and select final model/tokenizer | Final selection memo | Ablations |  | Not Started | High
7 | 51 | 53 | Engineering | Convert notebooks into scripts for corpus build, train, extract, score | scripts/ directory | Final selection |  | Not Started | High
7 | 53 | 55 | Engineering | Build monthly batch embedding pipeline | Batch inference pipeline | Scripts |  | Not Started | High
7 | 55 | 56 | Product | Create portfolio scoring demo and example output | Demo report | Scoring pipeline |  | Not Started | Medium
8 | 57 | 58 | Validation | Finalize benchmark evidence and limitations | Technical report | All results |  | Not Started | High
8 | 58 | 59 | Governance | Finalize model card and data card | model_card.md and data_card.md | Technical report |  | Not Started | High
8 | 59 | 60 | Project Mgmt | Package handoff and v2 roadmap | Final handoff pack | Model/data cards |  | Not Started | High

## Experiments
Experiment ID | Days | Model | Approx Params | Context | Tokenizer | Pooling / Evaluation | Purpose | Success Criteria | Status | Notes
E1 | 23-24 | Credit-TFM-S | ~30M | 2,048 | v1 | N/A | Pipeline validation | Loss decreases; no tokenizer bugs | Not Started
E2 | 25-27 | Credit-TFM-S | ~30M | 4,096 | v1 | Last-token | Baseline embedding | Embeddings usable in downstream models | Not Started
E3 | 28-31 | Credit-TFM-M | 100M-250M | 4,096 | v1 | Last-token + mean | Main candidate | Lift vs raw-feature baseline | Not Started
E4 | 30-34 | Credit-TFM-M | 100M-250M | 8,192 | v1 | Last-token + event-anchor | Long-history test | Improved lift or justified context choice | Not Started
E5 | 44-48 | Credit-TFM-M | 100M-250M | 4,096 | v2 | Best pooling from Phase 5 | Tokenizer v2 test | Improved metrics or simpler tokenizer | Not Started
E6 | 46-50 | Credit-TFM-M/L | 250M-1B optional | 8,192 | v2 | Best pooling | Final candidate / stretch | Best validation performance, no leakage | Not Started

## Metrics
Task | Dataset Split | Feature Set | Model | ROC-AUC | PR-AUC | KS | Gini | Brier | Lift@5% | Calibration Notes | Run Link
Default 3M | Validation | Raw features | XGBoost
Default 3M | Validation | Embeddings only | XGBoost
Default 3M | Validation | Raw + embeddings | XGBoost
Default 6M | Validation | Raw features | XGBoost
Default 6M | Validation | Embeddings only | XGBoost
Default 6M | Validation | Raw + embeddings | XGBoost
Prepay 6M | Validation | Raw features | LightGBM
Prepay 6M | Validation | Embeddings only | LightGBM
Prepay 6M | Validation | Raw + embeddings | LightGBM
Segmentation | Validation | Embeddings only | Clustering

## Risks
Risk ID | Risk | Severity | Likelihood | Mitigation | Owner | Status | Review Date | Notes
R1 | Data leakage from future-state fields | High | High | Observation-date feature store; field-level leakage inventory; temporal splits |  | Open
R2 | Weak baselines make foundation model lift misleading | High | Medium | Use strong XGBoost/LightGBM baselines and calibration checks |  | Open
R3 | Tokenizer over-compresses or over-expands credit events | Medium | High | Track sequence length, rare tokens, OOV, and run tokenizer ablations |  | Open
R4 | Overtraining / memorization on limited credit data | High | Medium | Start with 30M-250M; scale only if data volume and validation justify it |  | Open
R5 | Embeddings improve ranking but hurt calibration | Medium | Medium | Report calibration separately; recalibrate downstream models |  | Open
R6 | GPU time spent before dataset quality is proven | High | Medium | Enforce Phase 2 go/no-go gate before large pretraining |  | Open
R7 | Context window truncates important long-horizon behavior | Medium | Medium | Compare 2k/4k/8k and define windowing policy |  | Open

## Deliverables
Deliverable | Phase | Target Day | Artifact Type | Acceptance Criteria | Location / Link | Owner | Status | Notes
Credit event schema | 1 | 8 | Markdown / YAML | Events, entities, fields, and leakage exclusions documented | docs/credit_event_schema.md |  | Not Started
Baseline benchmark report | 2 | 14 | Notebook / Report | Includes ROC-AUC, PR-AUC, KS, Gini, calibration, lift@K | reports/baseline_report.md |  | Not Started
Credit tokenizer v1 | 3 | 22 | Python / YAML | Tokenizer generates train/val/test corpora and QA reports | src/tokenizer/credit_tokenizer.py |  | Not Started
Credit-TFM checkpoint | 4 | 34 | Model checkpoint | Stable validation loss and selected candidate config | checkpoints/ |  | Not Started
Embedding extraction pipeline | 5 | 37 | Script / Notebook | Produces embeddings for prediction points | scripts/extract_credit_embeddings.py |  | Not Started
Downstream evaluation report | 5 | 43 | Report | Compares raw, embeddings-only, raw+embeddings | reports/downstream_eval.md |  | Not Started
Ablation memo | 6 | 50 | Report | Documents tokenizer/model/pooling/context comparisons | reports/ablation_memo.md |  | Not Started
Batch scoring pipeline | 7 | 56 | Scripts | Repeatable monthly embedding and scoring pipeline | scripts/score_credit_portfolio.py |  | Not Started
Model card and data card | 8 | 59 | Governance docs | Intended use, limitations, data summary, risks | reports/model_card.md; reports/data_card.md |  | Not Started
Final handoff package | 8 | 60 | Report / Demo | Technical report, demo, and v2 roadmap complete | reports/final_handoff/ |  | Not Started

## Lists
Status | Priority | Severity | Likelihood
Not Started | Critical | Critical | High
In Progress | High | High | Medium
Blocked | Medium | Medium | Low
Done | Low | Low | Unknown
Deferred

## Sources
Source | Use | URL
NVIDIA AI Blueprint: Transaction Foundation Model | Reference implementation and workflow | https://github.com/NVIDIA-AI-Blueprints/transaction-foundation-model
NVIDIA blueprint README | Architecture, notebooks, tokenizer, embedding and evaluation workflow | https://raw.githubusercontent.com/NVIDIA-AI-Blueprints/transaction-foundation-model/main/README.md
NVIDIA pretrain config | Multi-GPU training command and config reference | https://raw.githubusercontent.com/NVIDIA-AI-Blueprints/transaction-foundation-model/main/configs/pretrain_financial_decoder.yaml